## Slide 1
FLEETPARTNERS · INTERNAL USE ONLY
Unaddressed Security Gaps Put FleetPartners at Material Risk of Breach,
Non-Compliance and Customer Attrition
A 12-Month Cybersecurity Strategy Roadmap to achieve ISO 27001:2022 alignment,
reduce exposure, and build enduring cyber resilience
FY27
Oct 2026 — Sep 2027
Framework
ISO 27001:2022
Classification
Confidential
Version
1.0 · Apr 2026
P
01

## Slide 2
THE CASE FOR ACTION
Four converging pressures make FY27 the critical window to act — delay compounds both risk and exposure
Regulatory & Customer Exposure
Inability to produce ISO 27001:2022 evidence suppresses contract wins. Enterprise clients increasingly mandate ISO compliance as a vendor qualification criterion — a gap FleetPartners cannot afford.
A.5.1
A.5.2
Maturity Rated 0.95 / 3.0 on ACSC Essential Eight
May 2023 assessment placed FleetPartners at Maturity Level 0.95 of 3 — well below the government-recommended Level 2. Critical attack vectors remain open: uncontrolled admin privileges, absent MFA, inconsistent patching.
A.8.5
A.8.8
Uncontrolled Privileged Access
No PAM controls; Linux servers use unmanaged local accounts; remote sessions via TeamViewer/RDP are unlogged. If a threat actor gains a foothold, lateral movement is trivially achievable — with no detection capability.
A.8.2
A.8.3
A.8.15
Policy–Practice Governance Gap
IT Policies exist on paper but governance mechanisms are absent. The IT Risk Register has been dormant since 2019. Without a functioning risk process, deviations go untracked — the precise condition auditors and breaches exploit.
A.5.1
A.5.5
A.5.6
0.95
Essential 8
Maturity
vs. recommended 2.0
22+
ISO 27001:2022
Control Gaps
across all domains
12mo
To Close
All Gaps
starting Oct 2026
P
02

## Slide 3
CURRENT STATE ASSESSMENT
Gaps span all four ISO 27001 control domains — demanding a structured, phased response
GOVERNANCE
IT Risk Register dormant since 2019
Policy governance not enforced
No formal BIA or Risk Assessment
No supplier risk process
9 mandatory docs absent
PEOPLE & ACCESS
No PAM — privileged access invisible
MFA not uniformly enforced
Linux servers on local accounts
Unmanaged service accounts
Security awareness training ad-hoc
INFRASTRUCTURE
No SIEM — zero detection capability
Unlogged remote access (RDP/SSH)
CVSS-only scoring — poor priority
No CMDB / asset lifecycle mgmt
Shared Wi-Fi key — never rotated
DATA & APPLICATIONS
No DLP — PII exfiltration undetectable
No data classification framework
No code scanning in CI/CD
No CSPM — cloud misconfiguration risk
No data flow diagrams
20+
CONTROL GAPS
4
DOMAINS AFFECTED
12mo
TO CLOSE
P
03

## Slide 4
12-MONTH ROADMAP · FY27
Four sequential phases transform FleetPartners from a reactive posture to ISO 27001:2022 alignment by September 2027
OCT 26
NOV
DEC
JAN 27
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP 27
Phase 1: Discovery & Governance
Phase 2: Core Controls
Phase 3: Hardening
Phase 4: Advanced Ops
Q1 FY27 · Oct – Dec 2026
Q2 FY27 · Jan – Mar 2027
Q3 FY27 · Apr – Jun 2027
Q4 FY27 · Jul – Sep 2027
PHASE 1
Discovery & Governance
Documentation framework
Data classification & CMDB
Risk assessment process
Asset management uplift
Security policy alignment
PHASE 2
Core Protective Controls
Identity & MFA consolidation
SIEM / log consolidation
Standard endpoint build
IT Risk Register revival
Security awareness training
PHASE 3
Hardening & Advanced Controls
PAM deployment
Jumphost / Bastion Host
Risk-based vuln management
CSPM & secure app dev
Network segmentation
PHASE 4
Advanced Defence & Operations
Data Loss Prevention (DLP)
BCDR & Incident Response
Annual penetration testing
Security metrics & ARC
Supplier risk management
P
04

## Slide 5
PHASE 1 · Q1 FY27 · OCT – DEC 2026
Without governance foundations, every control implemented later will drift — Phase 1 builds the baseline FleetPartners cannot skip
WHY IT MATTERS
No documentation = no auditability
9 mandatory ISO 27001:2022 documents are absent. Without a Support Matrix, onboarding/offboarding procedures, and configuration standards, FleetPartners cannot demonstrate compliance to auditors or customers.
A.5.1
A.5.3
A.6.1
PII exposure is unquantified
No data classification framework or data flow diagrams exist. FleetPartners cannot identify where PII resides or how it flows through MyCar, NAB SFTP, Power Automate, or HubSpot.
A.5.12
A.5.13
A.8.10
No risk management = no accountability
IT Risk Register dormant since 2019. IT changes proceed without documented risk acceptance, leaving FleetPartners unable to demonstrate due diligence in the event of a breach or audit.
A.5.5
A.5.6
A.5.7
HOW WE FIX IT
Create 9 mandatory ISO documents with annual review cycle — RACI, onboarding/offboarding, labelling, supplier register, HR screening, configuration standards
Data discovery & classification — map PII across all systems, design data lifecycle framework, create data flow diagrams for MyCar, NAB, cloud integrations
Revive IT Risk Register — JIRA triage workflow, time-limited exceptions with compensating controls, NFRC format for Risk Committee reporting
Deploy CMDB — leverage JIRA to track configuration baselines; enable accurate risk assessment for MACD requests
Conduct Business Impact Analysis — identify critical function recovery priorities and define RTO/RPO targets
DELIVERABLES
✓ 9 ISO documents created
✓ Data classification framework
✓ Data flow diagrams complete
✓ IT Risk Register active
✓ CMDB operational
✓ BIA completed
ISO CONTROLS
A.5.1
A.5.2
A.5.3
A.5.5
A.5.6
A.5.7
A.5.12
A.5.13
A.5.14
A.5.29
A.5.30
A.6.1
A.8.8
A.8.9
A.8.32
P
05

## Slide 6
PHASE 2 · Q2 FY27 · JAN – MAR 2027
Identity, visibility, and awareness controls are the highest-ROI investments FleetPartners can make — Phase 2 delivers them
WHY IT MATTERS
80% of breaches exploit weak identity controls
Linux servers on local accounts, no MFA enforcement, and no centralised identity governance leave every privileged credential as a potential breach entry point. Identity is the new perimeter — and it is unprotected.
A.5.15
A.5.16
A.8.5
Zero detection capability means zero response time
Without a SIEM, FleetPartners has no ability to detect anomalies, correlate security events, or perform DFIR after a breach. Logs from laptops, servers, and network devices exist in isolation — unmonitored and unretained.
A.8.15
A.8.16
A.5.25
Human error remains the #1 breach vector
Ad-hoc security awareness training leaves staff unprepared to recognise phishing, social engineering, and data handling violations. A structured program significantly reduces susceptibility rates.
A.6.3
A.6.8
HOW WE FIX IT
AD-join Linux servers — centralise identity, enable governance, eliminate unmanaged local accounts
MFA consolidation — enforce MFA across all systems, cloud services, VPN, and administrative access on a single platform
Deploy SIEM (e.g. Microsoft Sentinel / Splunk) — centralise log ingestion, define retention policy, configure alerting and JIRA integration
Standard SOE build — enforce uniform software via MDM/SCCM with whitelist; revise Wi-Fi to 802.1X RADIUS authentication
Security awareness program — role-based modules, monthly phishing simulations, mandatory annual refresher training
Revive IT Risk Register workflow — JIRA triage pipeline, exception management, Risk Committee reporting cadence
DELIVERABLES
✓ All Linux servers AD-joined
✓ MFA enforced enterprise-wide
✓ SIEM live with alerting
✓ SOE deployed to endpoints
✓ Awareness training launched
✓ Risk Register active
ISO CONTROLS
A.5.15
A.5.16
A.5.17
A.6.3
A.6.8
A.8.1
A.8.5
A.8.15
A.8.16
A.8.17
A.8.20
A.8.21
A.8.22
P
06

## Slide 7
PHASE 3 · Q3 FY27 · APR – JUN 2027
Privileged access is the highest-impact attack vector — Phase 3 eliminates it while hardening the full infrastructure layer
WHY IT MATTERS
Privileged accounts are invisible and uncontrolled
No PAM solution means privileged credentials are unknown, unrotated, and unmonitored. Remote server sessions via TeamViewer, RDP, and SSH leave no audit trail. A single compromised admin account can cause catastrophic damage.
A.8.2
A.8.3
A.8.15
A.6.6
Vulnerability management is effectively blind
Current tools cannot scan Kubernetes containers, and CVSS-only scoring fails to reflect real-world exploitability — making prioritisation impossible. The patching process lacks validation, producing an inconsistent cadence.
A.8.8
A.8.9
A.8.32
Cloud misconfigurations and insecure code go undetected
No CSPM means cloud configuration drift is invisible. No code scanning means applications ship with vulnerabilities. No API security controls means the attack surface expands with every new integration.
A.5.23
A.8.25
A.8.27
HOW WE FIX IT
Deploy PAM (e.g. CyberArk / BeyondTrust) — vault and rotate all privileged credentials, enable session recording for all administrative access
Implement Jumphost / Bastion Host — mandate all remote server access through a single audited gateway; eliminate direct RDP/SSH/TeamViewer
Upgrade vulnerability management (e.g. Rapid7 Exposure Command) — container scanning, risk-based prioritisation, revised patching workflow with validation
Deploy CSPM (e.g. Wiz / Prisma Cloud) — continuous cloud configuration monitoring, drift detection, compliance policy enforcement
Secure app dev pipeline — SAST/DAST (e.g. SonarQube), OWASP Top 10 API controls, architecture review gate, ASVS 5.0 adoption
Network segmentation — VLAN-based isolation of PCI, production, dev, corporate; firewall rule review and cleanup
DELIVERABLES
✓ PAM — all priv. accounts vaulted
✓ Jumphost deployed
✓ Risk-based vuln mgmt live
✓ CSPM monitoring cloud
✓ Code scanning in CI/CD
✓ Network segmentation done
ISO CONTROLS
A.5.23
A.6.6
A.8.1
A.8.2
A.8.3
A.8.4
A.8.5
A.8.8
A.8.9
A.8.15
A.8.20
A.8.22
A.8.25
A.8.27
A.8.29
P
07

## Slide 8
PHASE 4 · Q4 FY27 · JUL – SEP 2027
Advanced defence closes the final gaps — DLP, resilience, and continuous validation complete FleetPartners' ISO 27001:2022 posture
WHY IT MATTERS
Data exfiltration is currently undetectable
Without DLP controls, sensitive data and PII can leave FleetPartners via email, USB, cloud storage, or shadow IT — entirely undetected. Given FleetPartners' customer data obligations, this is a material regulatory and reputational risk.
A.8.10
A.8.12
A.5.14
No tested recovery plan for a cyber incident
BCDR plans have not been formalised or tested against cyber scenarios. RTO/RPO targets are undefined. If ransomware strikes, FleetPartners has no documented playbook, no assigned roles, and no validated recovery capability.
A.5.24
A.5.29
A.5.30
A.8.13
Controls have never been independently validated
No external penetration testing program exists. Controls implemented in Phases 1–3 will be untested until an adversary tests them. Annual CREST pen testing is the only way to validate effectiveness before attackers do.
A.5.35
A.5.36
A.8.8
HOW WE FIX IT
Deploy DLP (e.g. Microsoft Purview) — enforce data loss prevention across endpoint, network, and cloud; base policies on Phase 1 classification framework
Software Composition Analysis (SCA) — open-source dependency scanning, container image scanning, SBOM generation for all deployed applications
BCDR & Incident Response Plan — develop tested BCDR plans with defined RTO/RPO; document IRP with RACI and escalation paths; quarterly tabletop exercises
Annual CREST Penetration Testing — external/internal tests covering web application, API, and cloud infrastructure scope
Security metrics & ARC dashboard — executive KPIs/KRIs: patch SLAs, incident response times, training completion rates
Supplier risk management — security questionnaires, contractual security requirements, periodic reviews, supplier risk register
DELIVERABLES
✓ DLP active across all channels
✓ SCA in deployment pipeline
✓ BCDR plan tested
✓ IRP documented & rehearsed
✓ Pen test completed
✓ Security dashboard live
ISO CONTROLS
A.5.14
A.5.19
A.5.23
A.5.24
A.5.25
A.5.29
A.5.30
A.5.35
A.5.36
A.8.10
A.8.12
A.8.13
A.8.25
A.8.29
P
08

## Slide 9
EXPECTED OUTCOMES · BY SEP 2027
By completing all four phases, FleetPartners will transform from a reactive security posture to a defensible, audit-ready ISO 27001:2022 organisation
CURRENT STATE
✗ Essential 8 Maturity: 0.95 / 3.0
✗ ISO 27001 gaps: 22+ controls
✗ Risk Register: dormant since 2019
✗ Privileged access: uncontrolled
✗ Detection capability: none
✗ Data exfiltration visibility: zero
✗ Remote access logging: absent
✗ Customer compliance evidence: unable to provide
→
FY27 TARGET STATE
✓ Essential 8 Maturity: Target 2.0+
✓ ISO 27001 gaps: remediated
✓ Risk Register: active, reported monthly
✓ Privileged access: vaulted, audited, recorded
✓ Detection: SIEM live with 24/7 alerting
✓ DLP: endpoint, network & cloud covered
✓ Remote access: 100% via audited Jumphost
✓ Customer compliance: full evidence pack ready
STRATEGIC VALUE UNLOCKED
ISO 27001:2022 Readiness
Audit-ready posture to pursue ISO certification and win enterprise customer requirements
Customer RFP Wins
Complete security questionnaires and pass vendor due diligence for enterprise clients
Breach Cost Reduction
Organisations with security AI & automation detect and contain breaches significantly faster
Insurance Premiums
Demonstrated cyber maturity enables negotiation of lower cyber insurance premiums
P
09

## Slide 10
APPENDIX A
ISO 27001:2022 Annex A Controls — Gap-to-Control Mapping by Phase
Security Capability | ISO 27001:2022 Annex A Controls | Phase | Domain
Documentation & Governance | A.5.1 Policies, A.5.2 Roles, A.5.3 Segregation, A.5.13 Labelling, A.5.20 Supply Chain, A.6.1 Screening | P1 | Org
Data Classification | A.5.12 Classification, A.5.13 Labelling, A.8.10 Deletion, A.8.11 Masking, A.8.12 Leakage Prevention, A.5.14 Transfer | P1 | Tech
Risk Management & BIA | A.5.5 Threat Intelligence, A.5.6 Contact Authorities, A.5.7 Threat Sharing, A.5.29 ICT Continuity, A.5.30 Readiness | P1 | Org
Identity & Access | A.5.15 Access Control, A.5.16 Identity Mgmt, A.5.17 Auth Info, A.5.18 Access Rights, A.8.2 Privileged Access, A.8.5 Secure Auth | P2 / P3 | Org / Tech
Logging & Monitoring | A.8.15 Logging, A.8.16 Monitoring Activities, A.8.17 Clock Sync, A.5.25 Security Events Assessment | P2 | Tech
Vuln & Config Management | A.8.8 Technical Vulnerabilities, A.8.9 Configuration Management, A.8.32 Change Management | P3 | Tech
Secure Development | A.8.25 Secure Dev Policy, A.8.26 App Security, A.8.27 Secure Architecture, A.8.28 Secure Coding, A.8.29 Security Testing | P3 | Tech
Network Security | A.8.20 Network Security, A.8.21 Web Filtering, A.8.22 Segregation in Networks, A.8.23 Web Filtering | P3 | Tech
Cloud & Continuity | A.5.23 Cloud Security, A.5.29–A.5.30 ICT Continuity, A.8.13 Info Backup, A.8.14 Redundancy | P3 / P4 | Org / Tech
Incident & Supplier Mgmt | A.5.24–A.5.28 Incident Management, A.5.19–A.5.23 Supplier Security Requirements | P4 | Org
Reference: ISO 27001:2022 Annex A (93 controls, 4 themes) · https://www.isms.online/iso-27001
P
A-1

## Slide 11
APPENDIX B
ACSC Essential Eight — Deficiency Summary & Roadmap Alignment
Mitigation Strategy | Identified Gap | Phase | ISO Control
Application Control | No application whitelisting enforced | P1 | A.8.1
Patch Applications | Inconsistent patching cadence | P3 | A.8.8
Office Macro Configuration | Macro controls not enforced | P2 | A.8.1
User App Hardening | Browser hardening not standardised | P2 | A.8.26
Restrict Admin Privileges | PAM absent — admin usage uncontrolled | P3 | A.8.2
Patch Operating Systems | Inconsistent across server & endpoint fleets | P3 | A.8.8
Multi-Factor Authentication | Not uniformly enforced across all systems | P2 | A.8.5
Regular Backups | Backup testing & validation not formalised | P4 | A.8.13
MATURITY SCORE BY STRATEGY
Application Control
0
Patch Applications
1
Office Macro Configuration
1
User App Hardening
1
Restrict Admin Privileges
0
Patch Operating Systems
1
Multi-Factor Authentication
1
Regular Backups
1
Overall Maturity
0.95 / 3.0
Target: ≥ 2.0 by Sep 2027
Ref: https://www.cyber.gov.au/resources-business-and-government/essential-cybersecurity/essential-eight
P
A-2